## Project Plan
TASK ID | TASK | DESCRIPTION | DEPENDENCY | MILESTONE | % COMPLETE | STATUS
1 | Define standard user roles | Document all user personas, responsibilities, and access needs; create enterprise-wide role matrix. | None | Role Matrix Finalized | 20 | 20 | In Progress
2 | Create and configure secure AD access groups | Build AD groups aligned to defined roles; apply least-privilege access structure; validate membership. | Define standard user roles | AD Groups Created | 40 | 40 | In Progress
3 | Apply database-level security for all new AD groups | Implement DB, schema, and table permissions mapped to AD groups; enforce least privilege. | AD groups configured | Schema Access Restricted | 60 | 60 | In Progress
4 | Enable audit logging in Teradata | Activate auditing for logins, DDL/DML, admin actions, and security-related events. | None | Audit Logging Enabled | 5 | 5 | In Progress
5 | Implement role-based masking on PHI/PII data | Apply masking policies to sensitive data; validate per-role visibility in Dev/QA/Prod. | Database-level security | Masking Implemented | 0 | 0 | Not Started
6 | Expand governance and automation features | Add automation for onboarding, approval workflows, and governance controls. | Security controls established | Governance Improved | 0 | 0 | Not Started
7 | Restrict schema-level access | Tighten schema permissions to minimize exposure and strengthen governance. | Database-level security | Schema Governance Strengthened | 0 | 0 | Not Started
8 | Complete advanced security and compliance measures | Finalize compliance controls, align with auditors, and ensure regulatory readiness. | All previous tasks | Compliance Achieved | 0 | 0 | Not Started

## Roadmap
TASK ID | TASK | % COMPLETE
1 | Define standard user roles | 20
2 | Create and configure secure AD access groups | 40
3 | Apply database-level security for all new AD groups | 60
4 | Enable audit logging in Teradata | 6
5 | Implement role-based masking on PHI/PII data | 0
6 | Expand governance and automation features | 0
7 | Restrict schema-level access | 0
8 | Complete advanced security and compliance measures | 0

## Dashboard
Metric | Value
Total Tasks | 8
Completed Tasks | 0
In-Progress Tasks | 4
Not Started Tasks | 4
Average % Complete | 15.625